## timeline
EventID | EventName | StartYear | StartQuarter | EndYear | EndQuarter | Status
E001 | Atlas Core R&D | 2023 | Q1 | 2025 | Q4 | Completed
E002 | Atlas 1.0 Release | 2025 | Q3 | 2025 | Q3 | Completed
E003 | Atlas 1.x Support | 2025 | Q4 | 2027 | Q2 | On Schedule
E004 | Atlas 2.0 Development | 2026 | Q1 | 2027 | Q4 | On Schedule
E005 | Atlas 2.0 Release | 2028 | Q1 | 2028 | Q1 | Planned
E006 | Beacon UI Prototype | 2024 | Q2 | 2024 | Q4 | Completed
E007 | Beacon 1.0 Development | 2025 | Q1 | 2026 | Q2 | On Schedule
E008 | Beacon 1.0 Release | 2026 | Q3 | 2026 | Q3 | Planned
E009 | Beacon 1.x Enhancements | 2026 | Q4 | 2027 | Q4 | Planned
E010 | Cipher Engine Research | 2022 | Q3 | 2024 | Q1 | Completed
E011 | Cipher Engine 1.0 Release | 2024 | Q2 | 2024 | Q2 | Completed
E012 | Cipher 1.x Optimization | 2024 | Q3 | 2025 | Q4 | Completed
E013 | DeltaCloud Integration | 2025 | Q2 | 2026 | Q4 | Behind Schedule
E014 | DeltaCloud 2.0 Upgrade | 2027 | Q1 | 2028 | Q2 | Planned
E015 | Echo Services Pilot | 2026 | Q1 | 2026 | Q4 | On Schedule
E016 | Echo 1.0 Release | 2027 | Q1 | 2027 | Q1 | Planned
E017 | Echo 1.x Support | 2027 | Q2 | 2028 | Q4 | Planned
E018 | Fusion Platform R&D | 2027 | Q3 | 2029 | Q2 | Planned
E019 | Fusion 1.0 Release | 2029 | Q3 | 2029 | Q3 | Planned
E020 | Fusion 1.x Patch Cycle | 2029 | Q4 | 2030 | Q2 | Planned

## dependencies
Must Complete | Before the Start Of
E004 | E009
E004 | E005
E016 | E003